## Overview
Genesis ERP — Module-wise Delivery Workbook
Stack: Next.js 15 + Tailwind · NestJS 11 + Prisma + SQLite · e2e 73/73 passing (idempotent)
Status: Working = end-to-end complete · Partial = works with documented gaps · Mocked = infrastructure works, external delivery simulated
# | Phase | Module | Status | One-line summary | Key gaps
0 | 0 | Foundations (Auth & Branching) | Working | JWT auth, 5 roles, RolesGuard, branch_id scoping on every query, seed data. | No refresh tokens; no password reset flow.
1 | 1 | Admissions | Partial | 9-step workflow: Links Sent -> Submitted -> Validated -> Fee Approved -> Roll No -> VP Approved -> Admission Complete (creates Student). | Roll no is random, not [CLASS][YEAR][SEQ]; house random not balanced; documents stored as base64 in SQLite (2MB cap); no PDF letter rendering; notification mocked.
2 | 2 | Student Information System | Working | Full student CRUD with pagination, search, filters, status activation, profile with attendance/marks/hostel/fees; classes CRUD with delete guard. | Profile attendance % uses last 30 records only (documented).
3 | 3 | Parent Communication | Mocked | Central NotificationsService logs email/SMS/WhatsApp to notification_logs; all modules route through it; UI log viewer with channel filter. | Delivery is a console log in dev - swap NotificationsService.notify for MSG91/Twilio/SES in prod. No parent portal login.
4 | 4 | Fees | Working | Structures CRUD, per-term bulk invoice generation (idempotent), offline payments with overpay blocked, status rollup Unpaid -> Partially Paid -> Paid. | No payment gateway (offline entry by design); no receipts PDF; no discounts/scholarships.
5 | 5 | Attendance | Working | Batch marking per class/date, notify-absent flow, per-class % reports. | Student-profile % is last-30-records; no biometric/device integration; no leave-adjusted aggregates.
6 | 6 | Timetable & Substitution | Working | Teachers/rooms/periods CRUD, master timetable, school view, absence -> auto substitution generation, substitution management. | Generator is greedy, not constraint-optimised; no teacher preferences.
7 | 7 | Leave & Gate Pass | Working | Staff & student leave apply/approve/reject with role guards and email logging; gate pass lifecycle Pending -> Warden -> Principal -> Checked Out -> Returned with parent OTP enforcement. | OTP only 'sent' via mocked channel (visible in notification log); no leave balance accounting.
8 | 8 | Discipline & Safeguarding | Working | Incident CRUD with Open/Under Review/Closed, demerits, confidential notes; AuditLog on VIEW/CREATE/UPDATE/DELETE; admin-only audit log; strict role allow-list. | Hard delete allowed for admins (best practice: forbid); no parent notification on incident.
9 | 9 | Academics | Partial | Subjects CRUD (unique code, delete guard), syllabus units, lesson plans (topic/date/status), assignments publish with guardian notification. | Lesson-plan create form missing in UI (list only); no homework submission tracking.
10 | 10 | Reports & Dashboards | Working | Cross-module dashboard KPIs, per-class attendance %, fee collection summary, per-exam averages, hostel occupancy + payroll totals. | No CSV/PDF export; no trend charts over time.
11 | 11a | Hostel | Working | Hostels/rooms CRUD with delete guards, manual allocation (capacity enforced, move semantics), auto-allocation to freest room, visitor log with pass numbers and checkout guard. | No room-change history; no mess/attendance integration.
12 | 11b | Staff & Payroll | Partial | Staff CRUD with soft-deactivate on history, salary structure upsert, monthly payslip generation (idempotent) with unpaid-leave docking basic/30, TDS+EPF, mark-paid. | Flat TDS/EPF only - no Indian tax slabs/LWF/professional tax; no payslip PDF.
13 | 11c | CBT (Computer Based Tests) | Partial | Question bank (MCQ validation), test builder with ownership checks, publish lifecycle, server-authoritative timing (+5 min grace), answer-stripped papers, MCQ auto-grade, manual subjective grading queue, results. | No live countdown UI or tab-lock (server timing is enforced); no question media/images.

## 00 Foundations (Auth & Bran
00 · Foundations (Auth & Branching)
Delivery plan phase 0 · Status: Working
What works | JWT auth, 5 roles, RolesGuard, branch_id scoping on every query, seed data.
Backend endpoints | POST /api/auth/login; GET /api/auth/me; guard helpers
Frontend page | Login page; role badge in DashboardShell
e2e coverage | 5 tests (login ok/bad, me, 401s)
Honest gaps / to-production | No refresh tokens; no password reset flow.
Status fill: |  | Working (end-to-end) | Partial (works, documented gaps) | Mocked integration

## 01 Admissions
01 · Admissions
Delivery plan phase 1 · Status: Partial
What works | 9-step workflow: Links Sent -> Submitted -> Validated -> Fee Approved -> Roll No -> VP Approved -> Admission Complete (creates Student).
Backend endpoints | fields CRUD; trigger-links; :id/submit¦validate¦pay¦verify-receipt¦allocate¦vp-approve¦principal-approve; :id/documents CRUD; documents/:docId/download; :id/letter-data
Frontend page | Admissions page (existing)
e2e coverage | 12 tests incl. document upload/download and letter-data 403
Honest gaps / to-production | Roll no is random, not [CLASS][YEAR][SEQ]; house random not balanced; documents stored as base64 in SQLite (2MB cap); no PDF letter rendering; notification mocked.
Status fill: |  | Working (end-to-end) | Partial (works, documented gaps) | Mocked integration

## 02 Student Information Syst
02 · Student Information System
Delivery plan phase 2 · Status: Working
What works | Full student CRUD with pagination, search, filters, status activation, profile with attendance/marks/hostel/fees; classes CRUD with delete guard.
Backend endpoints | GET/POST /api/students; GET/PUT/DELETE /api/students/:id; PUT :id/status; classes CRUD
Frontend page | students/page.tsx (new): table, filters, pagination, add/edit modal, deactivate
e2e coverage | 7 tests (create, dup 409, invalid 400, pagination, update, status)
Honest gaps / to-production | Profile attendance % uses last 30 records only (documented).
Status fill: |  | Working (end-to-end) | Partial (works, documented gaps) | Mocked integration

## 03 Parent Communication
03 · Parent Communication
Delivery plan phase 3 · Status: Mocked
What works | Central NotificationsService logs email/SMS/WhatsApp to notification_logs; all modules route through it; UI log viewer with channel filter.
Backend endpoints | GET /api/notifications?ref_type¦recipient¦channel
Frontend page | notifications/page.tsx rewired to real API (was demo data)
e2e coverage | 2 tests (list, ref_type filter via leave decision)
Honest gaps / to-production | Delivery is a console log in dev - swap NotificationsService.notify for MSG91/Twilio/SES in prod. No parent portal login.
Status fill: |  | Working (end-to-end) | Partial (works, documented gaps) | Mocked integration

## 04 Fees
04 · Fees
Delivery plan phase 4 · Status: Working
What works | Structures CRUD, per-term bulk invoice generation (idempotent), offline payments with overpay blocked, status rollup Unpaid -> Partially Paid -> Paid.
Backend endpoints | structures CRUD; GET/POST invoices; POST invoices/generate; GET invoices/:id; POST payments
Frontend page | fees/page.tsx (new): structures tab + invoices tab with generate & record payment
e2e coverage | 2 tests (structures CRUD; lifecycle incl. overpay 409)
Honest gaps / to-production | No payment gateway (offline entry by design); no receipts PDF; no discounts/scholarships.
Status fill: |  | Working (end-to-end) | Partial (works, documented gaps) | Mocked integration

## 05 Attendance
05 · Attendance
Delivery plan phase 5 · Status: Working
What works | Batch marking per class/date, notify-absent flow, per-class % reports.
Backend endpoints | POST /api/attendance; GET /api/attendance; POST /api/attendance/notify-absent; GET /api/reports/attendance
Frontend page | attendance/page.tsx (existing, working)
e2e coverage | 4 tests
Honest gaps / to-production | Student-profile % is last-30-records; no biometric/device integration; no leave-adjusted aggregates.
Status fill: |  | Working (end-to-end) | Partial (works, documented gaps) | Mocked integration

## 06 Timetable & Substitution
06 · Timetable & Substitution
Delivery plan phase 6 · Status: Working
What works | Teachers/rooms/periods CRUD, master timetable, school view, absence -> auto substitution generation, substitution management.
Backend endpoints | teachers/rooms/periods CRUD; master/:classId; today/:classId; school-view; POST teachers/:id/absent; substitutions list/delete; slot PUT; substitute POST; generate POST
Frontend page | timetable pages incl. SubstitutionGrid (existing)
e2e coverage | 8 tests
Honest gaps / to-production | Generator is greedy, not constraint-optimised; no teacher preferences.
Status fill: |  | Working (end-to-end) | Partial (works, documented gaps) | Mocked integration

## 07 Leave & Gate Pass
07 · Leave & Gate Pass
Delivery plan phase 7 · Status: Working
What works | Staff & student leave apply/approve/reject with role guards and email logging; gate pass lifecycle Pending -> Warden -> Principal -> Checked Out -> Returned with parent OTP enforcement.
Backend endpoints | staff-leaves CRUD+decision; student-leaves CRUD+decision; gate-passes create/detail/approve-warden/approve-principal/checkout/checkin
Frontend page | leaves/page.tsx (new): 3 tabs, approve/reject actions, OTP check-in box
e2e coverage | 3 tests incl. wrong-OTP 400 and full lifecycle
Honest gaps / to-production | OTP only 'sent' via mocked channel (visible in notification log); no leave balance accounting.
Status fill: |  | Working (end-to-end) | Partial (works, documented gaps) | Mocked integration

## 08 Discipline & Safeguardin
08 · Discipline & Safeguarding
Delivery plan phase 8 · Status: Working
What works | Incident CRUD with Open/Under Review/Closed, demerits, confidential notes; AuditLog on VIEW/CREATE/UPDATE/DELETE; admin-only audit log; strict role allow-list.
Backend endpoints | GET/POST incidents; GET/PUT/DELETE incidents/:id; PUT :id/status; GET audit-log
Frontend page | discipline/page.tsx (new): report form, status dropdown, audit log modal (admin)
e2e coverage | 1 test (create/view-audited/status/audit-log/delete + invalid status 400)
Honest gaps / to-production | Hard delete allowed for admins (best practice: forbid); no parent notification on incident.
Status fill: |  | Working (end-to-end) | Partial (works, documented gaps) | Mocked integration

## 09 Academics
09 · Academics
Delivery plan phase 9 · Status: Partial
What works | Subjects CRUD (unique code, delete guard), syllabus units, lesson plans (topic/date/status), assignments publish with guardian notification.
Backend endpoints | subjects CRUD; syllabus CRUD; lesson-plans CRUD; assignments CRUD
Frontend page | academics/page.tsx (new): subjects/syllabus/plans/assignments tabs
e2e coverage | 4 tests
Honest gaps / to-production | Lesson-plan create form missing in UI (list only); no homework submission tracking.
Status fill: |  | Working (end-to-end) | Partial (works, documented gaps) | Mocked integration

## 10 Reports & Dashboards
10 · Reports & Dashboards
Delivery plan phase 10 · Status: Working
What works | Cross-module dashboard KPIs, per-class attendance %, fee collection summary, per-exam averages, hostel occupancy + payroll totals.
Backend endpoints | GET /api/reports/dashboard¦attendance¦fees¦academics¦summary
Frontend page | reports/page.tsx (new): KPI cards, fee tiles, attendance bars, exam averages
e2e coverage | 5 tests
Honest gaps / to-production | No CSV/PDF export; no trend charts over time.
Status fill: |  | Working (end-to-end) | Partial (works, documented gaps) | Mocked integration

## 11 Hostel
11 · Hostel
Delivery plan phase 11a · Status: Working
What works | Hostels/rooms CRUD with delete guards, manual allocation (capacity enforced, move semantics), auto-allocation to freest room, visitor log with pass numbers and checkout guard.
Backend endpoints | hostel CRUD; rooms CRUD; allocations list/create/delete; allocations/auto; visitors list/create/:id/checkout
Frontend page | hostel/page.tsx (new): hostels, rooms, allocations (manual+auto), visitor log
e2e coverage | 1 test (full lifecycle + double checkout 409)
Honest gaps / to-production | No room-change history; no mess/attendance integration.
Status fill: |  | Working (end-to-end) | Partial (works, documented gaps) | Mocked integration

## 12 Staff & Payroll
12 · Staff & Payroll
Delivery plan phase 11b · Status: Partial
What works | Staff CRUD with soft-deactivate on history, salary structure upsert, monthly payslip generation (idempotent) with unpaid-leave docking basic/30, TDS+EPF, mark-paid.
Backend endpoints | staff CRUD; GET/PUT salaries/:staffId; GET payslips; POST payslips/generate; PUT payslips/:id/mark-paid
Frontend page | staff/page.tsx (new): staff tab, salary tab, payroll tab with generate & mark-paid
e2e coverage | 2 tests incl. exact arithmetic (net 30550) and idempotency
Honest gaps / to-production | Flat TDS/EPF only - no Indian tax slabs/LWF/professional tax; no payslip PDF.
Status fill: |  | Working (end-to-end) | Partial (works, documented gaps) | Mocked integration

## 13 CBT (Computer Based Test
13 · CBT (Computer Based Tests)
Delivery plan phase 11c · Status: Partial
What works | Question bank (MCQ validation), test builder with ownership checks, publish lifecycle, server-authoritative timing (+5 min grace), answer-stripped papers, MCQ auto-grade, manual subjective grading queue, results.
Backend endpoints | questions CRUD; tests CRUD; publish/complete; tests/:id/start; tests/:id/submit; attempts/:id/grade; tests/:id/results
Frontend page | cbt/page.tsx (new): question bank, test builder, results & grading viewer
e2e coverage | 2 tests incl. auto-grade score 3 + manual grade -> 7, delete guard 409
Honest gaps / to-production | No live countdown UI or tab-lock (server timing is enforced); no question media/images.
Status fill: |  | Working (end-to-end) | Partial (works, documented gaps) | Mocked integration

## API Matrix
Module | Method | Path | Roles | Verified by e2e
Auth | POST | /api/auth/login | public | yes
Auth | GET | /api/auth/me | any authenticated | yes
Classes | GET/POST/PUT/DELETE | /api/classes(/:id) | admin (writes) | yes
Students | GET | /api/students (page, class_id, status, q) | any authenticated | yes
Students | POST/PUT/DELETE | /api/students(/:id, /:id/status) | admin/teacher (delete: admin) | yes
Admissions | GET/POST/DELETE | /api/admissions/fields(/:id) | any authenticated | yes
Admissions | POST | /api/admissions/trigger-links | any authenticated | yes
Admissions | POST | /api/admissions/:id/{submit,validate,pay,verify-receipt,allocate,vp-approve,principal-approve} | any authenticated | yes
Admissions | POST/GET/DELETE | /api/admissions/:id/documents, /api/admissions/documents/:docId(/download) | any authenticated | yes
Admissions | GET | /api/admissions/:id/letter-data | any authenticated (403 pre-approval) | yes
Notifications | GET | /api/notifications (ref_type, recipient, channel) | any authenticated | yes
Academics | CRUD | /api/academics/{subjects,syllabus,lesson-plans,assignments} | admin/teacher (writes) | yes
Fees | CRUD | /api/fees/structures(/:id) | admin | yes
Fees | GET/POST | /api/fees/invoices, /api/fees/invoices/generate | admin (writes) | yes
Fees | POST | /api/fees/payments | admin | yes
Attendance | GET/POST | /api/attendance, /api/attendance/notify-absent | any authenticated | yes
Timetable | CRUD+views | /api/timetable/... (teachers, rooms, periods, master, today, school-view, substitutions, generate) | role-dependent | yes
Exams | GET/POST | /api/exams, /api/exams/marks, /api/exams/reports/:studentId | any authenticated | yes
Leaves | GET/POST/PUT | /api/{staff,student}-leaves(/:id/decision) | decision: admin/principal(/warden) | yes
Gate Pass | GET/POST/PUT | /api/gate-passes(/:id, approve-warden, approve-principal, checkout, checkin) | warden/principal/admin | yes
Discipline | CRUD | /api/discipline/incidents(/:id, /:id/status) | restricted role set; delete: admin | yes
Discipline | GET | /api/discipline/audit-log | admin only | yes
Staff | CRUD | /api/staff(/:id) | admin (writes) | yes
Payroll | GET/PUT | /api/staff/salaries/:staffId, /api/staff/payslips | admin | yes
Payroll | POST/PUT | /api/staff/payslips/generate, /api/staff/payslips/:id/mark-paid | admin | yes
Hostel | CRUD | /api/hostel(/:id), /api/hostel/rooms(/:id) | admin (writes) | yes
Hostel | POST/DELETE | /api/hostel/allocations(/auto, /:id) | admin/warden | yes
Hostel | GET/POST/PUT | /api/hostel/visitors(/:id/checkout) | admin/warden | yes
Reports | GET | /api/reports/{dashboard,attendance,fees,academics,summary} | any authenticated | yes
CBT | CRUD | /api/cbt/questions(/:id) | admin/teacher | yes
CBT | CRUD+lifecycle | /api/cbt/tests(/:id, publish, complete) | admin/teacher | yes
CBT | POST | /api/cbt/tests/:id/{start,submit} | any authenticated (student_id) | yes
CBT | PUT/GET | /api/cbt/attempts/:id/grade, /api/cbt/tests/:id/results | admin/teacher | yes